CONFIDENTIAL – COMMERCIAL & PROJECT INFORMATION

WHMIS

Pharmaceutical Distribution ERP

Pre-Deployment Requirements & Payment Schedule

Project / System: WHMIS     •     Version 1.0     •     August 2026

| DEVELOPMENT / TECHNOLOGY PARTNER Virtual Wisdom Technologies Primary Contact: Muhammad Saad Mubeen Designation: Project Manager Email: pm@vwisdomtechnologies.com Phone: +92 318 5161571 | CLIENT Master Pharmaceuticals Representative: Mr. Jamil Ahmed Designation: [Insert Designation] Email: [Insert Email] Phone: [Insert Contact Number] Address: [Insert Address] |
| --- | --- |

Document Version 1.0   ·   August 2026   ·   Confidential – Commercial & Project Information

# Confidentiality Notice

This document is confidential and contains commercial and project information relating to the WHMIS system. It is prepared by Virtual Wisdom Technologies for Master Pharmaceuticals for the sole purpose of defining pre-deployment requirements, third-party costs and the associated payment schedule.

Its contents may not be copied, reproduced, distributed or disclosed to any third party, in whole or in part, without the prior written consent of both parties. By receiving this document, the recipient agrees to treat its contents as confidential.

Classification: Confidential – Commercial & Project Information.

# Contents

Right-click here and choose “Update Field” to build the contents.

# 1. Purpose of the Document

Virtual Wisdom Technologies has developed the existing Phase 1 of the WHMIS system for Master Pharmaceuticals. Master Pharmaceuticals has decided to operate the solution as a cloud-based, internet-accessible system so that authorized users can access it securely from anywhere over the internet.

The purpose of this document is to formally define:

Requirements that must be completed before production deployment.

Domain selection and registration.

Hosting plan selection.

Third-party domain and hosting charges.

Phase 1 deployment payment.

Remaining software development payment milestones.

Production deployment responsibilities.

Initial production go-live process.

Post-deployment support and maintenance responsibility.

Commercial dependencies affecting the implementation schedule.

Next contractual and operational steps.

Detailed software development scope and future module delivery are covered separately under the WHMIS System – Phase-Wise Development & Deployment Plan.

Detailed contractual matters, support terms, maintenance terms, service levels, intellectual property, confidentiality, warranties, change requests and other legal/commercial provisions will subsequently be governed through the applicable Service Agreement / Software Development Agreement / Support & Maintenance terms.

# 2. Production Deployment Approach

The WHMIS system will be deployed online so that authorized Master Pharmaceuticals users can access it securely through the internet. The production deployment will be managed by Virtual Wisdom Technologies.

Virtual Wisdom Technologies will handle all necessary technical deployment activities, including but not limited to:

Production server setup.

Application deployment.

Database deployment and configuration.

Domain connection and DNS configuration.

SSL/HTTPS configuration.

Application environment configuration.

Production security configuration.

Backup configuration.

Application storage configuration.

Required production-level technical settings.

Initial server/application monitoring setup.

Deployment testing.

Production verification.

Administrative access configuration.

Technical troubleshooting associated with deployment.

Master Pharmaceuticals only needs to approve three things 1. The selected domain. 2. The recommended hosting plan. 3. The applicable third-party charges. Infrastructure-level technical details — CPU, RAM, operating system, database engine, backup retention architecture, server configuration and similar parameters — are the responsibility of Virtual Wisdom Technologies. Master Pharmaceuticals is not required to select or understand them.

# 3. Domain Recommendations

Virtual Wisdom Technologies will provide approximately 3–4 suitable domain recommendations for Master Pharmaceuticals. The options below are placeholders and will be completed once domain research is finalised.

| Proposed Domain | Availability | First-Year Price | Renewal Price | Recommendation |
| --- | --- | --- | --- | --- |
| [Domain Option 1] | [To Be Checked] | PKR [Insert Current Price] | PKR [Insert Current Price] | [Recommendation] |
| [Domain Option 2] | [To Be Checked] | PKR [Insert Current Price] | PKR [Insert Current Price] | [Recommendation] |
| [Domain Option 3] | [To Be Checked] | PKR [Insert Current Price] | PKR [Insert Current Price] | [Recommendation] |
| [Domain Option 4] | [To Be Checked] | PKR [Insert Current Price] | PKR [Insert Current Price] | [Recommendation] |

Please note the following regarding domain registration:

Domain pricing is a third-party registrar charge.

Domain cost is separate from the PKR 300,000 software development and deployment fee.

Final domain availability must be verified immediately before purchase.

Domain prices may change at any time.

Promotional first-year prices may differ from renewal prices.

Renewal rates are determined by the registrar.

International vendor pricing may vary due to USD/PKR exchange-rate changes.

Applicable taxes or registrar fees may affect the final price.

Domain purchase will proceed after Master Pharmaceuticals approves one of the recommended options.

Where possible, the final domain will be registered under Master Pharmaceuticals’ ownership, or under an agreed ownership/account arrangement that ensures long-term client control.

# 4. Recommended Hosting Plan

Virtual Wisdom Technologies will identify and recommend a suitable production hosting plan for the WHMIS system. The recommendation is kept simple and commercial; the underlying infrastructure engineering is handled by Virtual Wisdom Technologies.

| Hosting Plan | Billing Period | First-Year Cost | Renewal Cost | Recommendation |
| --- | --- | --- | --- | --- |
| [Insert Provider] — [Insert Plan] | [Annual / Monthly] | PKR [Insert] | PKR [Insert] | Recommended for WHMIS Production Environment |

The recommended plan has been selected by Virtual Wisdom Technologies based on the application’s expected operational needs. Master Pharmaceuticals is not required to make technical infrastructure decisions; approval is only required for the selected plan and its cost.

# 5. What Virtual Wisdom Technologies Will Manage

After approval of the hosting and domain, Virtual Wisdom Technologies will take responsibility for the technical deployment and production configuration.

Production Deployment

Hosting setup.

Domain connection.

SSL/HTTPS setup.

Application deployment.

Database setup.

Required production configuration.

User/admin setup.

Deployment verification.

Production testing.

Go-live support.

Production Backup & Technical Configuration

Virtual Wisdom Technologies will configure and manage the required backup arrangements according to the selected hosting environment and project requirements. Master Pharmaceuticals is not required to define the backup architecture.

Technical Server Management

Virtual Wisdom Technologies will manage the technical configuration necessary for WHMIS to operate on the selected hosting environment. The client will not be required to manage production server-level settings unless otherwise mutually agreed.

# 6. Third-Party Vendor Charges

The following costs are separate from the WHMIS software development and deployment charges:

Domain registration.

Domain renewal.

Production hosting.

Hosting renewal.

Any separately approved premium third-party service introduced later.

These charges are payable based on the actual price charged by the applicable third-party provider.

Domain and hosting costs are not included in the PKR 300,000 development and deployment fee. Third-party vendor prices are subject to change according to vendor policies, promotional pricing, renewal pricing, applicable taxes, currency exchange-rate fluctuations and other charges imposed by the respective service provider. Virtual Wisdom Technologies does not control third-party pricing or renewal rates.

# 7. Total Development & Deployment Charges

Total Agreed Software Development & Deployment Value:  PKR 300,000

The amount is divided across four project phases:

| Phase | Scope | Amount |
| --- | --- | --- |
| Phase 1 | Existing WHMIS Core System – Production Deployment | PKR 100,000 |
| Phase 2 | HR, Employees & Payroll Module | PKR 60,000 |
| Phase 3 | Medical Representatives, Doctors & Field Visit Management | PKR 70,000 |
| Phase 4 | Doctor Activities, Financial Records, Samples, Integration & Final Enhancements | PKR 70,000 |
| Total | Complete Agreed Development & Deployment Scope | PKR 300,000 |

Note:  Domain registration, hosting and any approved third-party services are charged separately.

# 8. Payment Schedule

Milestone 1 – Phase 1

Amount:  PKR 100,000

Purpose:  Deployment of the currently completed Phase 1 WHMIS system into the production cloud environment.

Payment Due:  Before commencement/finalization of production deployment.

Phase 1 production deployment will proceed after:

Approval of this document.

Receipt of PKR 100,000 Phase 1 payment.

Approval of the selected domain.

Approval of the recommended hosting plan.

Payment/authorization of third-party domain and hosting charges.

Provision of any essential business information required for production setup.

Milestone 2 – Phase 2

Amount:  PKR 60,000

Scope:  HR, Employee and Payroll Module.

Payment Trigger:  Before commencement of Phase 2 development after completion/deployment of Phase 1 and authorization to proceed.

Milestone 3 – Phase 3

Amount:  PKR 70,000

Scope:  Medical Representative, Doctor and Field Visit Management.

Payment Trigger:  Before commencement of Phase 3 after review/acceptance of Phase 2 and authorization to proceed.

Milestone 4 – Phase 4

Amount:  PKR 70,000

Scope:  Doctor Activity & Financial Records, Sample Management, Integration and Final Enhancements.

Payment Trigger:  Before commencement of Phase 4 after review/acceptance of Phase 3 and authorization to proceed.

# 9. Payment Summary

| Phase 1 | PKR 100,000 |
| --- | --- |
| Phase 2 | PKR 60,000 |
| Phase 3 | PKR 70,000 |
| Phase 4 | PKR 70,000 |
| Total Software Development & Deployment | PKR 300,000 |
| Domain | Separate – Actual Vendor Cost |
| Hosting | Separate – Actual Vendor Cost |

# 10. Phase 1 Pre-Deployment & Go-Live Schedule

Assuming commercial approval, Phase 1 payment and domain/hosting approval are completed by 24 August 2026, the proposed schedule is:

| Date | Activity |
| --- | --- |
| 24 August 2026 | Commercial approval and Phase 1 payment confirmation |
| 24–25 August 2026 | Domain and hosting purchase/provisioning |
| 25–27 August 2026 | Production environment setup by Virtual Wisdom Technologies |
| 26–28 August 2026 | WHMIS application and database deployment |
| 28 August 2026 | Internal production verification |
| 29 August 2026 | Proposed Phase 1 production go-live |

These are proposed target dates. The dates above depend on timely payment, approvals and availability of required information. If the approval/payment date changes, the deployment timeline will move accordingly. 29 August 2026 is a proposed go-live target, not an unconditional contractual deadline.

# 11. Responsibilities of Virtual Wisdom Technologies

Virtual Wisdom Technologies will be responsible for:

Recommending suitable domain options.

Providing current domain pricing.

Recommending the production hosting plan.

Providing current hosting pricing.

Purchasing/configuring approved domain and hosting after client authorization/payment.

Production server setup.

Production application deployment.

Production database deployment.

Domain/DNS configuration.

SSL/HTTPS setup.

Backup configuration.

Production security configuration.

Application settings.

User/admin configuration as required.

Deployment QA.

Production testing.

Initial go-live technical support.

Resolving deployment-related technical issues.

Maintaining technical production configuration under the agreed support arrangement.

# 12. Responsibilities of Master Pharmaceuticals

Master Pharmaceuticals will be responsible for:

Reviewing and approving one of the proposed domains.

Approving the recommended hosting plan.

Paying the applicable domain and hosting vendor charges.

Paying the applicable software-development milestone.

Providing required authorized representative details.

Providing relevant company/business information required for WHMIS.

Providing required users/operational data where applicable.

Reviewing delivered functionality.

Providing timely and consolidated feedback.

Providing UAT/operational approval as required.

Master Pharmaceuticals is not responsible for technical server architecture, backups, SSL setup, database administration or production deployment configuration — these are handled by Virtual Wisdom Technologies.

# 13. Post-Deployment Support & Maintenance

Virtual Wisdom Technologies will also provide support and maintenance services for the deployed WHMIS system according to the mutually agreed support arrangement. The support and maintenance function may include:

Production application support.

Technical troubleshooting.

Correction of software defects within the supported deployed scope.

Deployment-related issue resolution.

Backup monitoring/management where applicable.

Production environment maintenance.

Basic security/configuration maintenance.

Application updates relating to the agreed system.

Assistance with system operational issues.

Restoration/support activities where technically required and available.

Coordination with the hosting/vendor where necessary.

Reasonable post-deployment technical assistance.

Included Support / Maintenance

Routine support and maintenance of the agreed deployed WHMIS system according to the final support arrangement.

Additional Development

New modules, substantial workflow changes, integrations, features or other enhancements outside the agreed development scope are not maintenance and will be treated as separate change requests or future development phases.

Support & Maintenance Commercial Terms To be documented in the final Service Agreement / Support & Maintenance Schedule.

# 14. Change Requests

PKR 300,000 represents the currently agreed development/deployment scope defined in the approved Phase-Wise Development & Deployment Plan. Any substantial new requirement will be treated as a Change Request and evaluated for:

Functional impact.

Technical impact.

Development effort.

Timeline impact.

Commercial impact.

No substantial additional development should be assumed to be included without written approval.

# 15. Taxes and External Charges

Applicable taxes, withholding deductions, banking charges or legally applicable government levies will be handled according to applicable law and the final invoice/payment arrangement.

# 16. Commercial Snapshot

Project: WHMIS Client: Master Pharmaceuticals Technology Partner: Virtual Wisdom Technologies Total Development & Deployment Charges: PKR 300,000 Phase 1: PKR 100,000 Phase 2: PKR 60,000 Phase 3: PKR 70,000 Phase 4: PKR 70,000 Domain: Separate third-party vendor cost Hosting: Separate third-party vendor cost Proposed Phase 1 Go-Live: 29 August 2026, subject to completion of prerequisites. Support & Maintenance: To be provided by Virtual Wisdom Technologies under the agreed support arrangement.

# 17. Next Steps

Approval of this Pre-Deployment Requirements & Payment Schedule.

Review of recommended domain options.

Selection and approval of domain.

Approval of recommended hosting plan.

Payment of domain and hosting vendor charges.

Payment of Phase 1 – PKR 100,000.

Production deployment by Virtual Wisdom Technologies.

Phase 1 go-live.

Commencement of Phase 2 according to the separate Phase-Wise Development & Deployment Plan.

Subsequent execution/finalization of Service Agreement and Support & Maintenance terms.

# 18. Acknowledgement & Sign-Off

By acknowledging this document, both parties confirm their understanding of the pre-deployment requirements, third-party domain and hosting costs, development payment milestones and proposed deployment process. Detailed software scope is governed by the approved Phase-Wise Development & Deployment Plan, while broader contractual and support terms will be covered under the applicable Service Agreement and Support & Maintenance arrangements.

For Virtual Wisdom Technologies Name: Muhammad Azhar Designation: [Insert] Signature: __________________________ Date: __________________________

For Master Pharmaceuticals Name: [Insert] Designation: [Insert] Signature: __________________________ Date: __________________________